## Summary
Requirements Traceability Matrix
One row per testcase and Test Cycle slot, plus one repository-only row for a testcase never added to a cycle. Cycle rows use the immutable testcase version pinned to that execution. Requirement IDs are testcase metadata; Functional Request is the mandatory request linked to the cycle. Summary cards cover the full current project; search and requirement filters refine the matrix rows.
Export details
Project | TQA-PROJ-02
Generated at | 2026-09-06 10:18
Requirement filter | all
Search | All records
Snapshot metrics
Test cases |  | Requirement mapped | Unmapped
50 |  | 50 | 0
Added to a cycle |  | Executed | Failed / Blocked
50 |  | 47 | 0
With defects
0

## Traceability Matrix
TQA-PROJ-02 Requirements Traceability Matrix
One row per testcase and Test Cycle slot, plus one repository-only row for a testcase never added to a cycle. Cycle rows use the immutable testcase version pinned to that execution. Requirement IDs are testcase metadata; Functional Request is the mandatory request linked to the cycle. Summary cards cover the full current project; search and requirement filters refine the matrix rows.
Epic ID | CR Number | Feature ID | User Story ID | Test Case ID | Test Case Version | Test Case Status | Module | Test Scenario | Functional Request | Test Cycle | Cycle Name | Cycle Status | Latest Result | Run Count | Executed At | Defect IDs | Defect Statuses
EP-QARM |  | FE-REQUEST | US-049 | TQA-TC-100 | 1.0 | Approved | QA Request Management | Validate successful QA request operation by Requester | TQA-FUNC-1909 | TQA-CYCLE-02 | Sanity Cycle | In Progress | Pass | 1 | 2026-09-06 10:17
EP-APPR |  | FE-APPROVAL | US-050 | TQA-TC-101 | 1.0 | Approved | Approval Workflow | Validate rejection of invalid or incomplete approval request data | TQA-FUNC-1909 | TQA-CYCLE-02 | Sanity Cycle | In Progress | Pass | 1 | 2026-09-06 10:17
EP-QARM |  | FE-REQUEST | US-001 | TQA-TC-52 | 1.0 | Approved | QA Request Management | Validate successful QA request operation by Requester | TQA-FUNC-1909 | TQA-CYCLE-02 | Sanity Cycle | In Progress | Not Executed | 0
EP-APPR |  | FE-APPROVAL | US-002 | TQA-TC-53 | 1.0 | Approved | Approval Workflow | Validate successful approval request operation by Department Head | TQA-FUNC-1909 | TQA-CYCLE-02 | Sanity Cycle | In Progress | Not Executed | 0
EP-TCM |  | FE-TESTCASE | US-003 | TQA-TC-54 | 1.0 | Approved | Test Case Management | Validate successful test case operation by QA Tester | TQA-FUNC-1909 | TQA-CYCLE-02 | Sanity Cycle | In Progress | Not Executed | 0
EP-TCY |  | FE-CYCLE | US-004 | TQA-TC-55 | 1.0 | Approved | Test Cycle Management | Validate successful test cycle operation by QA Tester | TQA-FUNC-1909 | TQA-CYCLE-02 | Sanity Cycle | In Progress | Pass | 1 | 2026-09-06 10:17
EP-EXEC |  | FE-EXECUTE | US-005 | TQA-TC-56 | 1.0 | Approved | Test Execution | Validate rejection of invalid or incomplete execution record data | TQA-FUNC-1909 | TQA-CYCLE-02 | Sanity Cycle | In Progress | Pass | 1 | 2026-09-06 10:17
EP-DEF |  | FE-DEFECT | US-006 | TQA-TC-57 | 1.0 | Approved | Defect Management | Validate successful defect operation by QA Tester | TQA-FUNC-1909 | TQA-CYCLE-02 | Sanity Cycle | In Progress | Pass | 1 | 2026-09-06 10:17
EP-USER |  | FE-RBAC | US-007 | TQA-TC-58 | 1.0 | Approved | User and Role Management | Validate successful user role operation by Administrator | TQA-FUNC-1909 | TQA-CYCLE-02 | Sanity Cycle | In Progress | Pass | 1 | 2026-09-06 10:17
EP-DASH |  | FE-DASHBOARD | US-008 | TQA-TC-59 | 1.0 | Approved | Dashboard | Validate successful dashboard operation by Department Head | TQA-FUNC-1909 | TQA-CYCLE-02 | Sanity Cycle | In Progress | Pass | 1 | 2026-09-06 10:17
EP-NOTIF |  | FE-NOTIFY | US-009 | TQA-TC-60 | 1.0 | Approved | Notifications | Validate successful notification operation by QA Lead | TQA-FUNC-1909 | TQA-CYCLE-02 | Sanity Cycle | In Progress | Pass | 1 | 2026-09-06 10:17
EP-DOC |  | FE-DOCUMENT | US-010 | TQA-TC-61 | 1.0 | Approved | Document Management | Validate rejection of invalid or incomplete document data | TQA-FUNC-1909 | TQA-CYCLE-02 | Sanity Cycle | In Progress | Pass | 1 | 2026-09-06 10:17
EP-AUDIT |  | FE-AUDIT | US-011 | TQA-TC-62 | 1.0 | Approved | Audit Trail | Validate successful audit entry operation by Administrator | TQA-FUNC-1909 | TQA-CYCLE-02 | Sanity Cycle | In Progress | Pass | 1 | 2026-09-06 10:17
EP-RPT |  | FE-REPORT | US-012 | TQA-TC-63 | 1.0 | Approved | Reports | Validate successful report operation by QA Lead | TQA-FUNC-1909 | TQA-CYCLE-02 | Sanity Cycle | In Progress | Pass | 1 | 2026-09-06 10:17
EP-QARM |  | FE-REQUEST | US-013 | TQA-TC-64 | 1.0 | Approved | QA Request Management | Validate successful QA request operation by Requester | TQA-FUNC-1909 | TQA-CYCLE-02 | Sanity Cycle | In Progress | Pass | 1 | 2026-09-06 10:17
EP-APPR |  | FE-APPROVAL | US-014 | TQA-TC-65 | 1.0 | Approved | Approval Workflow | Validate successful approval request operation by Department Head | TQA-FUNC-1909 | TQA-CYCLE-02 | Sanity Cycle | In Progress | Pass | 1 | 2026-09-06 10:17
EP-TCM |  | FE-TESTCASE | US-015 | TQA-TC-66 | 1.0 | Approved | Test Case Management | Validate rejection of invalid or incomplete test case data | TQA-FUNC-1909 | TQA-CYCLE-02 | Sanity Cycle | In Progress | Pass | 1 | 2026-09-06 10:17
EP-TCY |  | FE-CYCLE | US-016 | TQA-TC-67 | 1.0 | Approved | Test Cycle Management | Validate successful test cycle operation by QA Tester | TQA-FUNC-1909 | TQA-CYCLE-02 | Sanity Cycle | In Progress | Pass | 1 | 2026-09-06 10:17
EP-EXEC |  | FE-EXECUTE | US-017 | TQA-TC-68 | 1.0 | Approved | Test Execution | Validate successful execution record operation by QA Tester | TQA-FUNC-1909 | TQA-CYCLE-02 | Sanity Cycle | In Progress | Pass | 1 | 2026-09-06 10:17
EP-DEF |  | FE-DEFECT | US-018 | TQA-TC-69 | 1.0 | Approved | Defect Management | Validate successful defect operation by QA Tester | TQA-FUNC-1909 | TQA-CYCLE-02 | Sanity Cycle | In Progress | Pass | 1 | 2026-09-06 10:17
EP-USER |  | FE-RBAC | US-019 | TQA-TC-70 | 1.0 | Approved | User and Role Management | Validate successful user role operation by Administrator | TQA-FUNC-1909 | TQA-CYCLE-02 | Sanity Cycle | In Progress | Pass | 1 | 2026-09-06 10:17
EP-DASH |  | FE-DASHBOARD | US-020 | TQA-TC-71 | 1.0 | Approved | Dashboard | Validate rejection of invalid or incomplete dashboard data | TQA-FUNC-1909 | TQA-CYCLE-02 | Sanity Cycle | In Progress | Pass | 1 | 2026-09-06 10:17
EP-NOTIF |  | FE-NOTIFY | US-021 | TQA-TC-72 | 1.0 | Approved | Notifications | Validate successful notification operation by QA Lead | TQA-FUNC-1909 | TQA-CYCLE-02 | Sanity Cycle | In Progress | Pass | 1 | 2026-09-06 10:17
EP-DOC |  | FE-DOCUMENT | US-022 | TQA-TC-73 | 1.0 | Approved | Document Management | Validate successful document operation by Requester | TQA-FUNC-1909 | TQA-CYCLE-02 | Sanity Cycle | In Progress | Pass | 1 | 2026-09-06 10:17
EP-AUDIT |  | FE-AUDIT | US-023 | TQA-TC-74 | 1.0 | Approved | Audit Trail | Validate successful audit entry operation by Administrator | TQA-FUNC-1909 | TQA-CYCLE-02 | Sanity Cycle | In Progress | Pass | 1 | 2026-09-06 10:17
EP-RPT |  | FE-REPORT | US-024 | TQA-TC-75 | 1.0 | Approved | Reports | Validate successful report operation by QA Lead | TQA-FUNC-1909 | TQA-CYCLE-02 | Sanity Cycle | In Progress | Pass | 1 | 2026-09-06 10:17
EP-QARM |  | FE-REQUEST | US-025 | TQA-TC-76 | 1.0 | Approved | QA Request Management | Validate rejection of invalid or incomplete QA request data | TQA-FUNC-1909 | TQA-CYCLE-02 | Sanity Cycle | In Progress | Pass | 1 | 2026-09-06 10:17
EP-APPR |  | FE-APPROVAL | US-026 | TQA-TC-77 | 1.0 | Approved | Approval Workflow | Validate successful approval request operation by Department Head | TQA-FUNC-1909 | TQA-CYCLE-02 | Sanity Cycle | In Progress | Pass | 1 | 2026-09-06 10:17
EP-TCM |  | FE-TESTCASE | US-027 | TQA-TC-78 | 1.0 | Approved | Test Case Management | Validate successful test case operation by QA Tester | TQA-FUNC-1909 | TQA-CYCLE-02 | Sanity Cycle | In Progress | Pass | 1 | 2026-09-06 10:17
EP-TCY |  | FE-CYCLE | US-028 | TQA-TC-79 | 1.0 | Approved | Test Cycle Management | Validate successful test cycle operation by QA Tester | TQA-FUNC-1909 | TQA-CYCLE-02 | Sanity Cycle | In Progress | Pass | 1 | 2026-09-06 10:17
EP-EXEC |  | FE-EXECUTE | US-029 | TQA-TC-80 | 1.0 | Approved | Test Execution | Validate successful execution record operation by QA Tester | TQA-FUNC-1909 | TQA-CYCLE-02 | Sanity Cycle | In Progress | Pass | 1 | 2026-09-06 10:17
EP-DEF |  | FE-DEFECT | US-030 | TQA-TC-81 | 1.0 | Approved | Defect Management | Validate rejection of invalid or incomplete defect data | TQA-FUNC-1909 | TQA-CYCLE-02 | Sanity Cycle | In Progress | Pass | 1 | 2026-09-06 10:17
EP-USER |  | FE-RBAC | US-031 | TQA-TC-82 | 1.0 | Approved | User and Role Management | Validate successful user role operation by Administrator | TQA-FUNC-1909 | TQA-CYCLE-02 | Sanity Cycle | In Progress | Pass | 1 | 2026-09-06 10:17
EP-DASH |  | FE-DASHBOARD | US-032 | TQA-TC-83 | 1.0 | Approved | Dashboard | Validate successful dashboard operation by Department Head | TQA-FUNC-1909 | TQA-CYCLE-02 | Sanity Cycle | In Progress | Pass | 1 | 2026-09-06 10:17
EP-NOTIF |  | FE-NOTIFY | US-033 | TQA-TC-84 | 1.0 | Approved | Notifications | Validate successful notification operation by QA Lead | TQA-FUNC-1909 | TQA-CYCLE-02 | Sanity Cycle | In Progress | Pass | 1 | 2026-09-06 10:17
EP-DOC |  | FE-DOCUMENT | US-034 | TQA-TC-85 | 1.0 | Approved | Document Management | Validate successful document operation by Requester | TQA-FUNC-1909 | TQA-CYCLE-02 | Sanity Cycle | In Progress | Pass | 1 | 2026-09-06 10:17
EP-AUDIT |  | FE-AUDIT | US-035 | TQA-TC-86 | 1.0 | Approved | Audit Trail | Validate rejection of invalid or incomplete audit entry data | TQA-FUNC-1909 | TQA-CYCLE-02 | Sanity Cycle | In Progress | Pass | 1 | 2026-09-06 10:17
EP-RPT |  | FE-REPORT | US-036 | TQA-TC-87 | 1.0 | Approved | Reports | Validate successful report operation by QA Lead | TQA-FUNC-1909 | TQA-CYCLE-02 | Sanity Cycle | In Progress | Pass | 1 | 2026-09-06 10:17
EP-QARM |  | FE-REQUEST | US-037 | TQA-TC-88 | 1.0 | Approved | QA Request Management | Validate successful QA request operation by Requester | TQA-FUNC-1909 | TQA-CYCLE-02 | Sanity Cycle | In Progress | Pass | 1 | 2026-09-06 10:17
EP-APPR |  | FE-APPROVAL | US-038 | TQA-TC-89 | 1.0 | Approved | Approval Workflow | Validate successful approval request operation by Department Head | TQA-FUNC-1909 | TQA-CYCLE-02 | Sanity Cycle | In Progress | Pass | 1 | 2026-09-06 10:17
EP-TCM |  | FE-TESTCASE | US-039 | TQA-TC-90 | 1.0 | Approved | Test Case Management | Validate successful test case operation by QA Tester | TQA-FUNC-1909 | TQA-CYCLE-02 | Sanity Cycle | In Progress | Pass | 1 | 2026-09-06 10:17
EP-TCY |  | FE-CYCLE | US-040 | TQA-TC-91 | 1.0 | Approved | Test Cycle Management | Validate rejection of invalid or incomplete test cycle data | TQA-FUNC-1909 | TQA-CYCLE-02 | Sanity Cycle | In Progress | Pass | 1 | 2026-09-06 10:17
EP-EXEC |  | FE-EXECUTE | US-041 | TQA-TC-92 | 1.0 | Approved | Test Execution | Validate successful execution record operation by QA Tester | TQA-FUNC-1909 | TQA-CYCLE-02 | Sanity Cycle | In Progress | Pass | 1 | 2026-09-06 10:17
EP-DEF |  | FE-DEFECT | US-042 | TQA-TC-93 | 1.0 | Approved | Defect Management | Validate successful defect operation by QA Tester | TQA-FUNC-1909 | TQA-CYCLE-02 | Sanity Cycle | In Progress | Pass | 1 | 2026-09-06 10:17
EP-USER |  | FE-RBAC | US-043 | TQA-TC-94 | 1.0 | Approved | User and Role Management | Validate successful user role operation by Administrator | TQA-FUNC-1909 | TQA-CYCLE-02 | Sanity Cycle | In Progress | Pass | 1 | 2026-09-06 10:17
EP-DASH |  | FE-DASHBOARD | US-044 | TQA-TC-95 | 1.0 | Approved | Dashboard | Validate successful dashboard operation by Department Head | TQA-FUNC-1909 | TQA-CYCLE-02 | Sanity Cycle | In Progress | Pass | 1 | 2026-09-06 10:17
EP-NOTIF |  | FE-NOTIFY | US-045 | TQA-TC-96 | 1.0 | Approved | Notifications | Validate rejection of invalid or incomplete notification data | TQA-FUNC-1909 | TQA-CYCLE-02 | Sanity Cycle | In Progress | Pass | 1 | 2026-09-06 10:17
EP-DOC |  | FE-DOCUMENT | US-046 | TQA-TC-97 | 1.0 | Approved | Document Management | Validate successful document operation by Requester | TQA-FUNC-1909 | TQA-CYCLE-02 | Sanity Cycle | In Progress | Pass | 1 | 2026-09-06 10:17
EP-AUDIT |  | FE-AUDIT | US-047 | TQA-TC-98 | 1.0 | Approved | Audit Trail | Validate successful audit entry operation by Administrator | TQA-FUNC-1909 | TQA-CYCLE-02 | Sanity Cycle | In Progress | Pass | 1 | 2026-09-06 10:17
EP-RPT |  | FE-REPORT | US-048 | TQA-TC-99 | 1.0 | Approved | Reports | Validate successful report operation by QA Lead | TQA-FUNC-1909 | TQA-CYCLE-02 | Sanity Cycle | In Progress | Pass | 1 | 2026-09-06 10:17