## Summary
TQA-CYCLE-01 · Test Lifecycle
Complete selected-cycle snapshot with assignments, attempts, evidence, and defect links.
Export details
Cycle | Regression 1
Cycle ID | TQA-CYCLE-01
Project | TQA-PROJ-01 · CBS BANCS
Cycle status | Completed
Start date | 2026-08-19
End date | 2026-08-28
Generated by | QA 1
Generated at | 2026-08-23 17:01
Snapshot metrics
Testcases |  | Executed | Passed
2 |  | 2 | 2
Failed |  | Blocked | Unassigned
0 |  | 0 | 0
Attempts |  | Defect links | Evidence files
4 |  | 1 | 0

## Cycle Testcases
Cycle Testcases
One row per testcase slot; Latest Result mirrors the newest attempt.
Test Case ID | Version | Folder Path | Epic ID | CR Number | Feature ID | User Story ID | Test Type | Module | Priority | Scenario | Pre-Condition | Latest Result | Latest Actual Result | Latest Artifact | Latest Defect Summary | Assigned To | Assigned By | Assigned At | Last Runner | Last Run At | Attempt Count
TQA-TC-01 | 1.0 | CBS Core Banking / CBS Interface | EP-QARM |  | FE-REQUEST | US-001 | Function Positive | QA Request Management | Critical | Validate successful QA request operation by Requester | QA Portal test environment is available and a Requester test user exists. | Retest Passed |  |  | TQA-DEF-00001 | QA 1 | QA 1 | 2026-08-19 08:18 | QA 1 | 2026-08-19 08:33 | 2
TQA-TC-02 | 1.0 | CBS Core Banking / CBS Interface | EP-APPR |  | FE-APPROVAL | US-002 | Function Positive | Approval Workflow | High | Validate successful approval request operation by Department Head | QA Portal test environment is available and a Department Head test user exists. | Retest Passed |  |  |  | QA 1 | QA 1 | 2026-08-19 08:18 | QA 1 | 2026-08-19 08:33 | 2

## Test Steps
Test Steps
Definition used by each testcase in this cycle.
Test Case ID | Version | Step No | Step | Expected Result
TQA-TC-01 | 1.0 | 1 | Open the QA Portal and sign in as Requester. | The user is authenticated and the permitted landing page is displayed.
TQA-TC-01 | 1.0 | 2 | Navigate to QA Request Management and initiate the QA request operation. | The relevant form or action screen opens with role-based controls.
TQA-TC-01 | 1.0 | 3 | Enter valid mandatory data and complete the action. | The operation succeeds and a confirmation message is displayed.
TQA-TC-01 | 1.0 | 4 | Review the resulting status, list entry, notification, and audit history. | The saved data and workflow state are correct and traceable.
TQA-TC-02 | 1.0 | 1 | Open the QA Portal and sign in as Department Head. | The user is authenticated and the permitted landing page is displayed.
TQA-TC-02 | 1.0 | 2 | Navigate to Approval Workflow and initiate the approval request operation. | The relevant form or action screen opens with role-based controls.
TQA-TC-02 | 1.0 | 3 | Enter valid mandatory data and complete the action. | The operation succeeds and a confirmation message is displayed.
TQA-TC-02 | 1.0 | 4 | Review the resulting status, list entry, notification, and audit history. | The saved data and workflow state are correct and traceable.

## Execution Attempts
Execution Attempt History
Every retained execution attempt; later retests never overwrite earlier results.
Test Case ID | Attempt No | Result | Actual Result | Artifact | Defect Summary | Executed By | Executed At | Evidence Count | Evidence Files | History Note
TQA-TC-01 | 1 | Fail |  |  | TQA-DEF-00001 | QA 1 | 2026-08-19 08:18 | 0
TQA-TC-01 | 2 | Retest Passed |  |  |  | QA 1 | 2026-08-19 08:33 | 0
TQA-TC-02 | 1 | Fail |  |  |  | QA 1 | 2026-08-19 08:18 | 0
TQA-TC-02 | 2 | Retest Passed |  |  |  | QA 1 | 2026-08-19 08:33 | 0

## Defect Links
Structured Defect Links
Defects are tied to the exact execution attempt where they were observed.
Test Case ID | Attempt No | Defect Key | Defect URL | Title | Defect Status | Notes | Linked By | Linked At
TQA-TC-01 | 1 | TQA-DEF-00001 | /defects?open=TQA-DEF-00001 | defect 1d | Closed | Governed portal defect | QA 1 | 2026-08-19 08:19

## Evidence Index
Execution Evidence Index
Evidence metadata index. Binary files remain protected in the portal.
Test Case ID | Attempt No | File Name | Content Type | Size (KB) | Uploaded By | Uploaded At

## Cycle Activity
Cycle Activity History
Assignments, execution actions, defect links, and membership changes.
Activity | Decision | Actor | Role Snapshot | Comments | Timestamp
Cycle | Created | QA 1 | QA_ENGINEER | Created test cycle TQA-CYCLE-01 - Regression 1. | 2026-08-19 08:18
Lifecycle | Mark as Ready | QA 1 | QA_ENGINEER | Status changed from Draft to Ready. | 2026-08-19 08:18
Lifecycle | Start Execution | QA 1 | QA_ENGINEER | Status changed from Ready to In Progress. | 2026-08-19 08:18
Lifecycle | Complete Execution | QA 1 | QA_ENGINEER | Status changed from In Progress to Completed. | 2026-08-19 08:33
Request Link | Request Linked | QA 1 | QA_ENGINEER | Linked Functional request TQA-FUNC-02. | 2026-08-19 08:34
Request Link | Request Linked | QA 1 | QA_ENGINEER | Linked Functional request TQA-FUNC-01. Replaced Functional request TQA-FUNC-02. | 2026-08-19 08:34